## Schedule
Sprint #1 | Sprint #2 | Sprint #3 | Sprint #4 | DEMO
1
2
2
3
2
4
4
3
3
1
4
4
74.2267 | 65.16 | 57.59 | 50.98 | 247.9567

## Francisco
Original position | Avg | V | J | R | H | F | Related User Story | Task or Test
1 | 5.7 | 15 | 1.5 | 5 | 3 | 4 | Login | Login - Create a login page
2 | 0.98 | 0.5 | 0.3 | 3 | 0.1 | 1 | Login | Test 1: The page should contain a Login and Get Started Button visible in Google Chrome browser
3 | 0.98 | 0.5 | 0.3 | 3 | 0.1 | 1 | Login | Test 2: The page should contain “Helping Students Find Home Away From Home!” Heading.
4 | 6 | 10 | 2 | 5 | 5 | 8 | Login | Login - Integrate login with only @ucsd.edu mail id
5 | 1.58 | 0.5 | 0.3 | 3 | 0.1 | 4 | Login | Test 1: a ucsd email tries to login and it enters the website
6 | 1.18 | 0.5 | 0.3 | 3 | 0.1 | 2 | Login | Test 3: If user Authentication failed, allow the user at max two more re-tries to authenticate, if still fails, then show contact IT page.
7 | 1.22 | 0.5 | 0.5 | 3 | 0.1 | 2 | Login
8 | 1.9 | 1 | 1.5 | 1 | 3 | 3 | Login | Login - Write more tests
9 | 1.7 | 1 | 0.5 | 1 | 3 | 3 | Login | Login - Run tests
10 | 5.1 | 15 | 1.5 | 3 | 3 | 3 | Login | Login - Debugging
11 | 6.2 | 12 | 3 | 3 | 5 | 8 | Profile | Profile - Create user profiles with only information to be used when matching to a property. (Age, name, contact information, email, phone number, gender, etc) + there is a button to save edited information.
12 | 0.98 | 0.5 | 0.3 | 3 | 0.1 | 1 | Profile | Test 1: user can input their information into
13 | 0.96 | 0.5 | 0.2 | 3 | 0.1 | 1 | Profile | Profile Test 2: user can’t change his email
14 | 1.16 | 0.5 | 0.2 | 3 | 0.1 | 2 | Profile | Profile Test 3: the information get saved and can be shown after the page get refreshed
15 | 1.7 | 1 | 0.3 | 3 | 0.2 | 4 | Profile | Profile Test 4: The system should perform input field validators so it will only allow valid information to be pushed into the DB
16 | 1.16 | 0.5 | 0.2 | 3 | 0.1 | 2 | Profile | Profile Test 5: If the information is invalid, some warning/notification is shown to the user “please check your input, value X is invalid”.
17 | 1.16 | 0.5 | 0.2 | 3 | 0.1 | 2 | Profile | Profile Test 6: if the information is valid, a success message is displayed
18 | 3.5 | 3 | 3 | 5 | 3 |  | Profile | Profile - Account settings.
19 | 0.98 | 0.5 | 0.3 | 3 | 0.1 | 1 | Profile | Settings Test 1: User can access their profile page by clicking the icon.
20 | 1.19 | 0.5 | 0.3 | 3 | 0.15 | 2 | Profile | Settings Test 2: Fields of Name, Gender, Age, Phone can be editted and saved.
21 | 4.1 | 8 | 1.5 | 5 | 2 | 4 | Profile | Profile - Store for user profile input into database.
22 | 1.28 | 1 | 0.3 | 3 | 0.1 | 2 | Profile | Profile & DB Test 1: The system should perform input field validators so it will only allow valid information to be pushed into the DB.
23 | 1.68 | 1 | 0.3 | 3 | 0.1 | 4 | Profile | Profile & DB Test 2: When the user inputs his profile information/updates it, the database should be updated with his latest information only.
24 | 1.3 | 1 | 1.5 | 1 | 1 | 2 | Profile | Profile - Write more tests
25 | 1.1 | 1 | 0.5 | 1 | 1 | 2 | Profile | Profile - Run tests
26 | 3.6 | 10 | 2 | 3 | 1 | 2 | Profile | Profile - Debugging
27 | 6.1 | 10 | 2.5 | 5 | 5 | 8 | Database | Database Design - Entity relation model for database
28 | 2.1 | 2 | 0.5 | 3 | 3 | 2 | Database | Test1: Put some fake data in an excel spreadsheet and ask these questions to the DB:
29 | 3 |  |  | 5 | 2 | 2 | Database | Query of active users, can it be retrieved?
30 | 3 |  |  | 5 | 2 | 2 | Database | Query of particular id of housing, can it be retrieved?
31 | 2.6667 |  |  | 5 | 2 | 1 | Database | Test: Query of all users
32 | 6.2 | 10 | 3 | 5 | 5 | 8 | Database | Database - Implement it on PostgreSQL
33 | 1.86 | 1 | 0.3 | 3 | 3 | 2 | Database | Test: Tables are created based on the entity relation model
34 | 5.9 | 12 | 1.5 | 5 | 3 | 8 | Database | Database - Make the connection between the database and the frontend
35 | 2.6 | 3 | 1 | 5 | 3 | 1 | Database | Database - Save information for filters.
36 | 1.5 | 1 | 1.5 | 1 | 2 | 2 | Database | Database - Write more tests
37 | 1.3 | 1 | 0.5 | 1 | 2 | 2 | Database | Database - Run tests
38 | 3.8 | 10 | 2 | 3 | 2 | 2 | Database | Database - Debugging
39 | 5.6 | 12 | 3 | 5 | 2 | 6 | Search | Search and Sort - Design a search bar with filter and sort.
40 | 1.36 | 0.5 | 0.3 | 3 | 1 | 2 | Search | Test 1: The search bar section contains a search button, a filter section with a number of filters and an apply button, and a sort button.
41 | 2.9 | 3 | 0.5 | 5 | 2 | 4 | Search | Search - define the query to send to the database with the selected filters
42 | 1.56 | 1 | 0.3 | 3 | 1.5 | 2 | Search | Test 1: The query sent to the database matches the content in search and filter.
43 | 2.5 | 2 | 0.5 | 5 | 1 | 4 | Search | Search - send the query to the database
44 | 1.36 | 0.5 | 0.3 | 3 | 1 | 2 | Search | Test 1: The database does have the query being sent.
45 | 3.6 | 5 | 1 | 5 | 5 | 2 | Search | Search - return the query results to the frontend. Do a single inquiry for search results. 10 per page. Get all 10 property information.
46 | 1.66 | 1 | 0.3 | 3 | 2 | 2 | Search | Test 1: All of the query results and information are sent to the frontend correctly.
47 | 1.06 | 0.5 | 0.3 | 3 | 1 | 0.5 | Search | Test 2: All of the results are displayed with a button to show detailed information and each page has 10 apartments.
48 | 3.7 | 5 | 2.5 | 5 | 2 | 4 | Search | Search - Display the searched results on the frontend 10 at a time as lists.
49 | 0.9 | 0.5 | 0.4 | 3 | 0.1 | 0.5 | Search | Test1: click the search button and the result shows in the webpage.
50 | 0.88 | 0.5 | 0.3 | 3 | 0.1 | 0.5 | Search | Test2: the information is displayed clearly with no overlapping
51 | 1.34 | 1 | 1.5 | 1 | 0.2 | 3 | Search | Search - Write more tests
52 | 1.14 | 1 | 0.5 | 1 | 0.2 | 3 | Search | Search - Run tests
53 | 4.64 | 10 | 2 | 3 | 0.2 | 8 | Search | Search - Debugging
54 | 5.4 | 10 | 2 | 5 | 5 | 5 | Filter | Filter - Apply preferences in searching (# of bedrooms, # of bathrooms, price, commute time to UCSD, size of apartment [sqft] and rating)
55 | 1.28 | 0.5 | 0.4 | 3 | 2 | 0.5 | Filter | Test: saving
56 | 2.76 | 2 | 0.8 | 5 | 3 | 3 | Filter | Filter - Implement button to clear the current filter
57 | 1.66 | 0.5 | 0.3 | 3 | 4 | 0.5 | Filter | Test: when having a set of filter active and clicking the “clear” button, all the filters disappear and the webpage looks like the homepage
58 | 3.4 | 2 | 2 | 5 | 4 | 4 | Filter | Filter - Add values. Tentative list : Location, commute time, type of apartment/house, types of roommates, range of housing price, neighborhood, number of bedrooms and bathrooms, size of apartments in sqft, ranking and reviews of apartments
59 | 1.66 | 1 | 0.3 | 1 | 2 | 4 | Filter | Test 1 : Validate filter input
60 | 2.9 | 2 | 2.5 | 5 | 4 | 1 | Filter | Filter - Design how to display filtered values
61 | 1.3 | 1 | 1.5 | 1 | 2 | 1 | Filter | Filter - Write more tests
62 | 1.3 | 1 | 0.5 | 1 | 2 | 2 | Filter | Filter - Run tests
63 | 2.6 | 3 | 2 | 3 | 2 | 3 | Filter | Filter - Debugging
64 | 6.1 | 10 | 2.5 | 5 | 9 | 4 | Map | Map - Integrate google map
65 | 1.56 | 1 | 0.3 | 3 | 3 | 0.5 | Map | Test: when clicking in the button a new window appears with the google map website displaying the location of the property and its address
66 | 1.6 | 1 | 1 | 1 | 3 | 2 | Map | Map - Write more tests
67 | 1.26 | 1 | 0.3 | 1 | 2 | 2 | Map | Map - Run tests
68 | 2.2 | 3 | 1 | 3 | 2 | 2 | Map | Map - Debugging
69 | 6.6 | 15 | 4 | 5 | 5 | 4 | Details | Details - Display picture, blurb, website link, email, phone number, filter values, prices, past prices, ratings, reviews.
70 | 1.86 | 2 | 0.8 | 3 | 3 | 0.5 | Details | Test: After clicking on one apartments, you can see in a new webpage the picture, website link of the owner, email of the owner, phone number of the owner, price of the property, past prices in a table, average rating and reviews.
71 | 1.5 | 1 | 1.5 | 1 | 2 | 2 | Details | Details - Write more tests
72 | 1.3 | 1 | 0.5 | 1 | 2 | 2 | Details | Details - Run tests
73 | 3.3 | 8 | 1.5 | 3 | 2 | 2 | Details | Details - Debugging
74 | 5.3 | 10 | 2.5 | 5 | 5 | 4 | Rating | Rating & Reviews - display average rating for the clicked property, and display all the reviews and each review’s associated rating for the property.
75 | 1.16 | 1 | 0.3 | 3 | 1 | 0.5 | Rating | Test1: average rating is displayed and computed correctly of the property.
76 | 1.16 | 1 | 0.3 | 3 | 1 | 0.5 | Rating | Test2: All reviews are displayed in the correct format, and each review has its associated rating.
77 | 1.3 | 1 | 1.5 | 1 | 1 | 2 | Rating | Rating & Reviews - Write more tests
78 | 1.1 | 1 | 0.5 | 1 | 1 | 2 | Rating | Rating & Reviews - Run tests
79 | 3.5 | 10 | 1.5 | 3 | 1 | 2 | Rating | Rating & Reviews - Debugging
80 | 3.5 | 6 | 2.5 | 5 | 2 | 2 | Prices historical | Prices - display a table that shows the current and previous rating of the apartment.
81 | 1.16 | 1 | 0.3 | 3 | 1 | 0.5 | Prices historical | Test: current and previous ratings are displayed in the correct format.
82 | 1 | 1 | 1 | 1 | 1 | 1 | Prices historical | Prices - Write more tests
83 | 0.88 | 1 | 0.4 | 1 | 1 | 1 | Prices historical | Prices - Run tests
84 | 1.8 | 3 | 1 | 3 | 1 | 1 | Prices historical | Prices - Debugging
85 | 4.1 | 8 | 1.5 | 5 | 4 | 2 | Tenant Input | Tenant Input Prices, & Reviews- The student inputs a review, then to assembly the query to send to the DB
86 | 3 | 3 | 1 | 5 | 4 | 2 | Tenant Input | Tenant input & Reviews- Send the input review + rating to the database from the assembled query
87 | 2.8 | 2 | 1 | 5 | 4 | 2 | Tenant Input | Tenant Input - Update the database with the review and the rating sent
88 | 1.36 | 1 | 0.3 | 3 | 2 | 0.5 | Tenant Input | Test1: updates can be seen in the tables
89 | 1.4 | 1 | 1 | 1 | 2 | 2 | Tenant Input | Tenant Input - Write more tests
90 | 1.26 | 1 | 0.3 | 1 | 2 | 2 | Tenant Input | Tenant Input - Run tests
91 | 2.6 | 5 | 1 | 3 | 2 | 2 | Tenant Input | Tenant Input - Debugging
92 | 3.2 | 5 | 1 | 5 | 2 | 3 | Sort | Sort - sort the displayed apartments based on the average rating.
93 | 1.16 | 1 | 0.3 | 3 | 1 | 0.5 | Sort | Test1 : apartments displayed are in descending order based on the average rating.
94 | 3.2 | 5 | 1 | 5 | 2 | 3 | Sort | Sort - sort the displayed apartments based on the price(high to low/low to high).
95 | 1.16 | 1 | 0.3 | 3 | 1 | 0.5 | Sort | Test1 : apartments displayed are in ascending order or descending order based on the price.
96 | 1.2 | 1 | 1 | 1 | 1 | 2 | Sort | Sort - Write more tests
97 | 1.08 | 1 | 0.4 | 1 | 1 | 2 | Sort | Sort - Run tests
98 | 2.4 | 5 | 1 | 3 | 1 | 2 | Sort | Sort - Debugging
99 | 4.5 | 10 | 2.5 | 5 | 3 | 2 | Likes | Likes - Create a star (favorite) list for users.
100 | 1.16 | 1 | 0.3 | 3 | 1 | 0.5 | Likes | Test 1: webpage of star list is created and can be accessed by users.
101 | 3.2 | 3 | 1 | 5 | 3 | 4 | Likes | Likes - User can star apartments that they like and find them in their own star list.
102 | 1.16 | 1 | 0.3 | 3 | 1 | 0.5 | Likes | Test 1: User can see the apartments page that they star in the list.
103 | 2 | 1 | 1 | 1 | 1 | 6 | Likes | Likes - Write more tests

## Bhavya
Estimate [hours] | Task or Test
5 | Login - Create a login page
3 | Test 1: The page should contain a Login and Get Started Button visible in Google Chrome browser
3 | Test 2: The page should contain “Helping Students Find Home Away From Home!” Heading.
5 | Login - Integrate login via google with only ucsd.edu .
3 | Test 1: a ucsd email tries to login and it enters the website
3 | Test 2: a non-ucsd email tries to login and fails
3 | Test 3: If user Authentication failed, allow the user at max two more re-tries to authenticate, if still fails, then show contact IT page.
1 | Login - Write more tests
1 | Login - Run tests
3 | Login - Debugging
3 | Profile - Create user profiles with only information to be used when matching to a property. (Age, name, contact information, email, phone number, gender, etc) + there is a button to save edited information.
3 | Test 1: user can input their information into
3 | Test 2: user can’t change his email
3 | Test 3: the information get saved and can be shown after the page get refreshed
3 | Test 4: The system should perform input field validators so it will only allow valid information to be pushed into the DB
3 | Test 5: If the information is invalid, some warning/notification is shown to the user “please check your input, value X is invalid”.
3 | Test 6: if the information is valid, a success message is displayed
5 | Profile - Account settings.
3 | Test 1: User can access their profile page by clicking the icon.
3 | Test 2: Fields of Name, Gender, Age, Phone can be editted and saved.
5 | Profile - Store for user profile input into database.
3 | Test 1: The system should perform input field validators so it will only allow valid information to be pushed into the DB.
3 | Test 2: When the user inputs his profile information/updates it, the database should be updated with his latest information only.
1 | Profile - Write more tests
1 | Profile - Run tests
3 | Profile - Debugging
5 | Database Design - Entity relation model for database
3 | Test1: Put some fake data in an excel spreadsheet and ask these questions to the DB:
5 | Query of active users, can it be retrieved?
5 | Query of particular id of housing, can it be retrieved?
5 | Query of
5 | Database - Implement it on PostgreSQL
3 | Test: Tables are created based on the entity relation model
5 | Database - Make the connection between the database and the frontend
5 | Database - Save information for filters.
1 | Database - Write more tests
1 | Database - Run tests
3 | Database - Debugging
5 | Search and Sort - Design a search bar with filter and sort.
3 | Test 1: The search bar section contains a search button, a filter section with a number of filters and an apply button, and a sort button.
5 | Search - define the query to send to the database with the selected filters
3 | Test 1: The query sent to the database matches the content in search and filter.
5 | Search - send the query to the database
3 | Test 1: The database does have the query being sent.
5 | Search - return the query results to the frontend. Do a single inquiry for search results. 10 per page. Get all 10 property information.
3 | Test 1: All of the query results and information are sent to the frontend correctly.
3 | Test 2: All of the results are displayed with a button to show detailed information and each page has 10 apartments.
5 | Search - Display the searched results on the frontend 10 at a time as lists.
3 | Test1: click the search button and the result shows in the webpage.
3 | Test2: the information is displayed clearly with no overlapping
1 | Search - Write more tests
1 | Search - Run tests
3 | Search - Debugging
5 | Filter - Apply preferences in searching (# of bedrooms, # of bathrooms, price, commute time to UCSD, size of apartment [sqft] and rating)
3 | Test: saving
5 | Filter - Implement button to clear the current filter
3 | Test: when having a set of filter active and clicking the “clear” button, all the filters disappear and the webpage looks like the homepage
5 | Filter - Add values. Tentative list : Location, commute time, type of apartment/house, types of roommates, range of housing price, neighborhood, number of bedrooms and bathrooms, size of apartments in sqft, ranking and reviews of apartments
1 | Test 1 : Validate filter input
5 | Filter - Design how to display filtered values
1 | Filter - Write more tests
1 | Filter - Run tests
3 | Filter - Debugging
5 | Map - Integrate google map
3 | Test: when clicking in the button a new window appears with the google map website displaying the location of the property and its address
1 | Map - Write more tests
1 | Map - Run tests
3 | Map - Debugging
5 | Details - Display picture, blurb, website link, email, phone number, filter values, prices, past prices, ratings, reviews.
3 | Test: After clicking on one apartments, you can see in a new webpage the picture, website link of the owner, email of the owner, phone number of the owner, price of the property, past prices in a table, average rating and reviews.
1 | Details - Write more tests
1 | Details - Run tests
3 | Details - Debugging
5 | Rating & Reviews - display average rating for the clicked property, and display all the reviews and each review’s associated rating for the property.
3 | Test1: average rating is displayed and computed correctly of the property.
3 | Test2: All reviews are displayed in the correct format, and each review has its associated rating.
1 | Rating & Reviews - Write more tests
1 | Rating & Reviews - Run tests
3 | Rating & Reviews - Debugging
5 | Prices - display a table that shows the current and previous rating of the apartment.
3 | Test: current and previous ratings are displayed in the correct format.
1 | Prices - Write more tests
1 | Prices - Run tests
3 | Prices - Debugging
5 | Tenant Input Prices, & Reviews- The student inputs a review, then to assembly the query to send to the DB
5 | Tenant input & Reviews- Send the input review + rating to the database from the assembled query
5 | Tenant Input - Update the database with the review and the rating sent
3 | Test1: updates can be seen in the tables
1 | Tenant Input - Write more tests
1 | Tenant Input - Run tests
3 | Tenant Input - Debugging
5 | Sort - sort the displayed apartments based on the average rating.
3 | Test1 : apartments displayed are in descending order based on the average rating.
5 | Sort - sort the displayed apartments based on the price(high to low/low to high).
3 | Test1 : apartments displayed are in ascending order or descending order based on the price.
1 | Sort - Write more tests
1 | Sort - Run tests
3 | Sort - Debugging
5 | Likes - Create a star (favorite) list for users.
3 | Test 1: webpage of star list is created and can be accessed by users.
5 | Likes - User can star apartments that they like and find them in their own star list.
3 | Test 1: User can see the apartments page that they star in the list.
1 | Likes - Write more tests
1 | Likes - Run tests
3 | Likes - Debugging

## Hari
Estimate [hours] | Task or Test
3 | Login - Create a login page
0.1 | Test 1: The page should contain a Login and Get Started Button visible in Google Chrome browser
0.1 | Test 2: The page should contain “Helping Students Find Home Away From Home!” Heading.
5 | Login - Integrate login via google with only ucsd.edu .
0.1 | Test 1: a ucsd email tries to login and it enters the website
0.1 | Test 2: a non-ucsd email tries to login and fails
0.1 | Test 3: If user Authentication failed, allow the user at max two more re-tries to authenticate, if still fails, then show contact IT page.
3 | Login - Write more tests
3 | Login - Run tests
3 | Login - Debugging
5 | Profile - Create user profiles with only information to be used when matching to a property. (Age, name, contact information, email, phone number, gender, etc) + there is a button to save edited information.
0.1 | Test 1: user can input their information into
0.1 | Test 2: user can’t change his email
0.1 | Test 3: the information get saved and can be shown after the page get refreshed
0.2 | Test 4: The system should perform input field validators so it will only allow valid information to be pushed into the DB
0.1 | Test 5: If the information is invalid, some warning/notification is shown to the user “please check your input, value X is invalid”.
0.1 | Test 6: if the information is valid, a success message is displayed
3 | Profile - Account settings.
0.1 | Test 1: User can access their profile page by clicking the icon.
0.15 | Test 2: Fields of Name, Gender, Age, Phone can be editted and saved.
2 | Profile - Store for user profile input into database.
0.1 | Test 1: The system should perform input field validators so it will only allow valid information to be pushed into the DB.
0.1 | Test 2: When the user inputs his profile information/updates it, the database should be updated with his latest information only.
1 | Profile - Write more tests
1 | Profile - Run tests
1 | Profile - Debugging
5 | Database Design - Entity relation model for database
3 | Test1: Put some fake data in an excel spreadsheet and ask these questions to the DB:
2 | Query of active users, can it be retrieved?
2 | Query of particular id of housing, can it be retrieved?
2 | Query of
5 | Database - Implement it on PostgreSQL
3 | Test: Tables are created based on the entity relation model
3 | Database - Make the connection between the database and the frontend
3 | Database - Save information for filters.
2 | Database - Write more tests
2 | Database - Run tests
2 | Database - Debugging
2 | Search and Sort - Design a search bar with filter and sort.
1 | Test 1: The search bar section contains a search button, a filter section with a number of filters and an apply button, and a sort button.
2 | Search - define the query to send to the database with the selected filters
1.5 | Test 1: The query sent to the database matches the content in search and filter.
1 | Search - send the query to the database
1 | Test 1: The database does have the query being sent.
5 | Search - return the query results to the frontend. Do a single inquiry for search results. 10 per page. Get all 10 property information.
2 | Test 1: All of the query results and information are sent to the frontend correctly.
1 | Test 2: All of the results are displayed with a button to show detailed information and each page has 10 apartments.
2 | Search - Display the searched results on the frontend 10 at a time as lists.
0.1 | Test1: click the search button and the result shows in the webpage.
0.1 | Test2: the information is displayed clearly with no overlapping
0.2 | Search - Write more tests
0.2 | Search - Run tests
0.2 | Search - Debugging
5 | Filter - Apply preferences in searching (# of bedrooms, # of bathrooms, price, commute time to UCSD, size of apartment [sqft] and rating)
2 | Test: saving
3 | Filter - Implement button to clear the current filter
4 | Test: when having a set of filter active and clicking the “clear” button, all the filters disappear and the webpage looks like the homepage
4 | Filter - Add values. Tentative list : Location, commute time, type of apartment/house, types of roommates, range of housing price, neighborhood, number of bedrooms and bathrooms, size of apartments in sqft, ranking and reviews of apartments
2 | Test 1 : Validate filter input
4 | Filter - Design how to display filtered values
2 | Filter - Write more tests
2 | Filter - Run tests
2 | Filter - Debugging
9 | Map - Integrate google map
3 | Test: when clicking in the button a new window appears with the google map website displaying the location of the property and its address
3 | Map - Write more tests
2 | Map - Run tests
2 | Map - Debugging
5 | Details - Display picture, blurb, website link, email, phone number, filter values, prices, past prices, ratings, reviews.
3 | Test: After clicking on one apartments, you can see in a new webpage the picture, website link of the owner, email of the owner, phone number of the owner, price of the property, past prices in a table, average rating and reviews.
2 | Details - Write more tests
2 | Details - Run tests
2 | Details - Debugging
5 | Rating & Reviews - display average rating for the clicked property, and display all the reviews and each review’s associated rating for the property.
1 | Test1: average rating is displayed and computed correctly of the property.
1 | Test2: All reviews are displayed in the correct format, and each review has its associated rating.
1 | Rating & Reviews - Write more tests
1 | Rating & Reviews - Run tests
1 | Rating & Reviews - Debugging
2 | Prices - display a table that shows the current and previous rating of the apartment.
1 | Test: current and previous ratings are displayed in the correct format.
1 | Prices - Write more tests
1 | Prices - Run tests
1 | Prices - Debugging
4 | Tenant Input Prices, & Reviews- The student inputs a review, then to assembly the query to send to the DB
4 | Tenant input & Reviews- Send the input review + rating to the database from the assembled query
4 | Tenant Input - Update the database with the review and the rating sent
2 | Test1: updates can be seen in the tables
2 | Tenant Input - Write more tests
2 | Tenant Input - Run tests
2 | Tenant Input - Debugging
2 | Sort - sort the displayed apartments based on the average rating.
1 | Test1 : apartments displayed are in descending order based on the average rating.
2 | Sort - sort the displayed apartments based on the price(high to low/low to high).
1 | Test1 : apartments displayed are in ascending order or descending order based on the price.
1 | Sort - Write more tests
1 | Sort - Run tests
1 | Sort - Debugging
3 | Likes - Create a star (favorite) list for users.
1 | Test 1: webpage of star list is created and can be accessed by users.
3 | Likes - User can star apartments that they like and find them in their own star list.
1 | Test 1: User can see the apartments page that they star in the list.
1 | Likes - Write more tests

## Vincent
Estimate [hours] | Task or Test
15 | Login - Create a login page
0.5 | Test 1: The page should contain a Login and Get Started Button visible in Google Chrome browser
0.5 | Test 2: The page should contain “Helping Students Find Home Away From Home!” Heading.
10 | Login - Integrate login via google with only ucsd.edu .
0.5 | Test 1: a ucsd email tries to login and it enters the website
0.5 | Test 2: a non-ucsd email tries to login and fails
0.5 | Test 3: If user Authentication failed, allow the user at max two more re-tries to authenticate, if still fails, then show contact IT page.
1 | Login - Write more tests
1 | Login - Run tests
15 | Login - Debugging
12 | Profile - Create user profiles with only information to be used when matching to a property. (Age, name, contact information, email, phone number, gender, etc) + there is a button to save edited information.
0.5 | Test 1: user can input their information into
0.5 | Test 2: user can’t change his email
0.5 | Test 3: the information get saved and can be shown after the page get refreshed
1 | Test 4: The system should perform input field validators so it will only allow valid information to be pushed into the DB
0.5 | Test 5: If the information is invalid, some warning/notification is shown to the user “please check your input, value X is invalid”.
0.5 | Test 6: if the information is valid, a success message is displayed
3 | Profile - Account settings.
0.5 | Test 1: User can access their profile page by clicking the icon.
0.5 | Test 2: Fields of Name, Gender, Age, Phone can be editted and saved.
8 | Profile - Store for user profile input into database.
1 | Test 1: The system should perform input field validators so it will only allow valid information to be pushed into the DB.
1 | Test 2: When the user inputs his profile information/updates it, the database should be updated with his latest information only.
1 | Profile - Write more tests
1 | Profile - Run tests
10 | Profile - Debugging
10 | Database Design - Entity relation model for database
2 | Test1: Put some fake data in an excel spreadsheet and ask these questions to the DB:
Query of active users, can it be retrieved?
Query of particular id of housing, can it be retrieved?
Query of
10 | Database - Implement it on PostgreSQL
1 | Test: Tables are created based on the entity relation model
12 | Database - Make the connection between the database and the frontend
3 | Database - Save information for filters.
1 | Database - Write more tests
1 | Database - Run tests
10 | Database - Debugging
12 | Search and Sort - Design a search bar with filter and sort.
0.5 | Test 1: The search bar section contains a search button, a filter section with a number of filters and an apply button, and a sort button.
3 | Search - define the query to send to the database with the selected filters
1 | Test 1: The query sent to the database matches the content in search and filter.
2 | Search - send the query to the database
0.5 | Test 1: The database does have the query being sent.
5 | Search - return the query results to the frontend. Do a single inquiry for search results. 10 per page. Get all 10 property information.
1 | Test 1: All of the query results and information are sent to the frontend correctly.
0.5 | Test 2: All of the results are displayed with a button to show detailed information and each page has 10 apartments.
5 | Search - Display the searched results on the frontend 10 at a time as lists.
0.5 | Test1: click the search button and the result shows in the webpage.
0.5 | Test2: the information is displayed clearly with no overlapping
1 | Search - Write more tests
1 | Search - Run tests
10 | Search - Debugging
10 | Filter - Apply preferences in searching (# of bedrooms, # of bathrooms, price, commute time to UCSD, size of apartment [sqft] and rating)
0.5 | Test: saving
2 | Filter - Implement button to clear the current filter
0.5 | Test: when having a set of filter active and clicking the “clear” button, all the filters disappear and the webpage looks like the homepage
2 | Filter - Add values. Tentative list : Location, commute time, type of apartment/house, types of roommates, range of housing price, neighborhood, number of bedrooms and bathrooms, size of apartments in sqft, ranking and reviews of apartments
1 | Test 1 : Validate filter input
2 | Filter - Design how to display filtered values
1 | Filter - Write more tests
1 | Filter - Run tests
3 | Filter - Debugging
10 | Map - Integrate google map
1 | Test: when clicking in the button a new window appears with the google map website displaying the location of the property and its address
1 | Map - Write more tests
1 | Map - Run tests
3 | Map - Debugging
15 | Details - Display picture, blurb, website link, email, phone number, filter values, prices, past prices, ratings, reviews.
2 | Test: After clicking on one apartments, you can see in a new webpage the picture, website link of the owner, email of the owner, phone number of the owner, price of the property, past prices in a table, average rating and reviews.
1 | Details - Write more tests
1 | Details - Run tests
8 | Details - Debugging
10 | Rating & Reviews - display average rating for the clicked property, and display all the reviews and each review’s associated rating for the property.
1 | Test1: average rating is displayed and computed correctly of the property.
1 | Test2: All reviews are displayed in the correct format, and each review has its associated rating.
1 | Rating & Reviews - Write more tests
1 | Rating & Reviews - Run tests
10 | Rating & Reviews - Debugging
6 | Prices - display a table that shows the current and previous rating of the apartment.
1 | Test: current and previous ratings are displayed in the correct format.
1 | Prices - Write more tests
1 | Prices - Run tests
3 | Prices - Debugging
8 | Tenant Input Prices, & Reviews- The student inputs a review, then to assembly the query to send to the DB
3 | Tenant input & Reviews- Send the input review + rating to the database from the assembled query
2 | Tenant Input - Update the database with the review and the rating sent
1 | Test1: updates can be seen in the tables
1 | Tenant Input - Write more tests
1 | Tenant Input - Run tests
5 | Tenant Input - Debugging
5 | Sort - sort the displayed apartments based on the average rating.
1 | Test1 : apartments displayed are in descending order based on the average rating.
5 | Sort - sort the displayed apartments based on the price(high to low/low to high).
1 | Test1 : apartments displayed are in ascending order or descending order based on the price.
1 | Sort - Write more tests
1 | Sort - Run tests
5 | Sort - Debugging
10 | Likes - Create a star (favorite) list for users.
1 | Test 1: webpage of star list is created and can be accessed by users.
3 | Likes - User can star apartments that they like and find them in their own star list.
1 | Test 1: User can see the apartments page that they star in the list.
1 | Likes - Write more tests

## Jesse
Estimate [hours] | Task or Test
1.5 | Login - Create a login page
0.3 | Test 1: The page should contain a Login and Get Started Button visible in Google Chrome browser
0.3 | Test 2: The page should contain “Helping Students Find Home Away From Home!” Heading.
2 | Login - Integrate login via google with only ucsd.edu .
0.3 | Test 1: a ucsd email tries to login and it enters the website
0.3 | Test 2: a non-ucsd email tries to login and fails
0.5 | Test 3: If user Authentication failed, allow the user at max two more re-tries to authenticate, if still fails, then show contact IT page.
1.5 | Login - Write more tests
0.5 | Login - Run tests
1.5 | Login - Debugging
3 | Profile - Create user profiles with only information to be used when matching to a property. (Age, name, contact information, email, phone number, gender, etc) + there is a button to save edited information.
0.3 | Test 1: user can input their information into
0.2 | Test 2: user can’t change his email
0.2 | Test 3: the information get saved and can be shown after the page get refreshed
0.3 | Test 4: The system should perform input field validators so it will only allow valid information to be pushed into the DB
0.2 | Test 5: If the information is invalid, some warning/notification is shown to the user “please check your input, value X is invalid”.
0.2 | Test 6: if the information is valid, a success message is displayed
3 | Profile - Account settings.
0.3 | Test 1: User can access their profile page by clicking the icon.
0.3 | Test 2: Fields of Name, Gender, Age, Phone can be editted and saved.
1.5 | Profile - Store for user profile input into database.
0.3 | Test 1: The system should perform input field validators so it will only allow valid information to be pushed into the DB.
0.3 | Test 2: When the user inputs his profile information/updates it, the database should be updated with his latest information only.
1.5 | Profile - Write more tests
0.5 | Profile - Run tests
2 | Profile - Debugging
2.5 | Database Design - Entity relation model for database
0.5 | Test1: Put some fake data in an excel spreadsheet and ask these questions to the DB:
Query of active users, can it be retrieved?
Query of particular id of housing, can it be retrieved?
Query of
3 | Database - Implement it on PostgreSQL
0.3 | Test: Tables are created based on the entity relation model
1.5 | Database - Make the connection between the database and the frontend
1 | Database - Save information for filters.
1.5 | Database - Write more tests
0.5 | Database - Run tests
2 | Database - Debugging
3 | Search and Sort - Design a search bar with filter and sort.
0.3 | Test 1: The search bar section contains a search button, a filter section with a number of filters and an apply button, and a sort button.
0.5 | Search - define the query to send to the database with the selected filters
0.3 | Test 1: The query sent to the database matches the content in search and filter.
0.5 | Search - send the query to the database
0.3 | Test 1: The database does have the query being sent.
1 | Search - return the query results to the frontend. Do a single inquiry for search results. 10 per page. Get all 10 property information.
0.3 | Test 1: All of the query results and information are sent to the frontend correctly.
0.3 | Test 2: All of the results are displayed with a button to show detailed information and each page has 10 apartments.
2.5 | Search - Display the searched results on the frontend 10 at a time as lists.
0.4 | Test1: click the search button and the result shows in the webpage.
0.3 | Test2: the information is displayed clearly with no overlapping
1.5 | Search - Write more tests
0.5 | Search - Run tests
2 | Search - Debugging
2 | Filter - Apply preferences in searching (# of bedrooms, # of bathrooms, price, commute time to UCSD, size of apartment [sqft] and rating)
0.4 | Test: saving
0.8 | Filter - Implement button to clear the current filter
0.3 | Test: when having a set of filter active and clicking the “clear” button, all the filters disappear and the webpage looks like the homepage
2 | Filter - Add values. Tentative list : Location, commute time, type of apartment/house, types of roommates, range of housing price, neighborhood, number of bedrooms and bathrooms, size of apartments in sqft, ranking and reviews of apartments
0.3 | Test 1 : Validate filter input
2.5 | Filter - Design how to display filtered values
1.5 | Filter - Write more tests
0.5 | Filter - Run tests
2 | Filter - Debugging
2.5 | Map - Integrate google map
0.3 | Test: when clicking in the button a new window appears with the google map website displaying the location of the property and its address
1 | Map - Write more tests
0.3 | Map - Run tests
1 | Map - Debugging
4 | Details - Display picture, blurb, website link, email, phone number, filter values, prices, past prices, ratings, reviews.
0.8 | Test: After clicking on one apartments, you can see in a new webpage the picture, website link of the owner, email of the owner, phone number of the owner, price of the property, past prices in a table, average rating and reviews.
1.5 | Details - Write more tests
0.5 | Details - Run tests
1.5 | Details - Debugging
2.5 | Rating & Reviews - display average rating for the clicked property, and display all the reviews and each review’s associated rating for the property.
0.3 | Test1: average rating is displayed and computed correctly of the property.
0.3 | Test2: All reviews are displayed in the correct format, and each review has its associated rating.
1.5 | Rating & Reviews - Write more tests
0.5 | Rating & Reviews - Run tests
1.5 | Rating & Reviews - Debugging
2.5 | Prices - display a table that shows the current and previous rating of the apartment.
0.3 | Test: current and previous ratings are displayed in the correct format.
1 | Prices - Write more tests
0.4 | Prices - Run tests
1 | Prices - Debugging
1.5 | Tenant Input Prices, & Reviews- The student inputs a review, then to assembly the query to send to the DB
1 | Tenant input & Reviews- Send the input review + rating to the database from the assembled query
1 | Tenant Input - Update the database with the review and the rating sent
0.3 | Test1: updates can be seen in the tables
1 | Tenant Input - Write more tests
0.3 | Tenant Input - Run tests
1 | Tenant Input - Debugging
1 | Sort - sort the displayed apartments based on the average rating.
0.3 | Test1 : apartments displayed are in descending order based on the average rating.
1 | Sort - sort the displayed apartments based on the price(high to low/low to high).
0.3 | Test1 : apartments displayed are in ascending order or descending order based on the price.
1 | Sort - Write more tests
0.4 | Sort - Run tests
1 | Sort - Debugging
2.5 | Likes - Create a star (favorite) list for users.
0.3 | Test 1: webpage of star list is created and can be accessed by users.
1 | Likes - User can star apartments that they like and find them in their own star list.
0.3 | Test 1: User can see the apartments page that they star in the list.
1 | Likes - Write more tests